## Feuille1
Week	Goals	Comments
Week 1	General Project Description / Verification of the faisability of the algorithm	Goals and means of the project understood. Read main papers on the subject / Algorithm is ergodic (ask Paolo for more details). Detailed balance is ok.
Week 2	Design algorithm flow / Design class diagrams / Identifiy needed data structures / Identify needed input / Identify wanted outputs	Two verions proposed / In progress / To do, after algorithm structure fixed / Ok. Discuss with Paolo / Ok. Discuss with Paolo
Week 3	Implementation, step 1 / Class implementation / Unitary tests
Week 4	Implementation, step 2 / Class implemetation / Unitary tests / Global code structure overview
Week 5	Runs with no VE : simple pivot and new algo / Compare number of elem. Operations needed to obtain Nconf conformations / Compare decorrelation time between the 2 algos
Week 6	Runs with VE : same operations as without VE
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14